# Board Meeting – Briefing Notes

Prepared by the Executive Director for the meeting on Wednesday 18 November 2026. Draft – internal.

# 1. Headlines

Survey fieldwork is about 55% complete. Tranche 2 is delayed by permissions in two districts; we expect to finish by end of January 2027.

Nine of twelve focus group discussions done and transcribed. Early themes: economic pressure is now the main lens through which people talk about reconciliation; young people more open to contact across communities but distrustful of institutions.

Young Researchers Programme on track. Third mentoring workshop held in Kandy in September.

Finance: spend at about 76% of the annual budget (LKR 51.4m of 67.9m) against 83% expected at end-October, mostly because fieldwork payments have slipped. Cash is tight in December–January until tranche 3 arrives.

First full year as an independent organisation: audit firm appointed, finance policies being formalised.

# 2. Finance (from the Finance & Administration Manager)

Underspends: survey fieldwork (timing), report design and printing (report due Q1 2027), community dialogues (two moved to November).

Overspends to explain to the donor: transcription and anonymisation (more FGD hours than planned, and one possible duplicate payment under review), field travel for young researchers, translation of outputs.

Data analysis software paid upfront for the year – timing, not an overspend.

Shared cost allocation: one cost line is allocated at only 95% – being corrected.

Cash flow: closing balance expected to go below the 2-month operating reserve in January 2027. Tranche 3 depends on the interim report being accepted.

Audit: expenditure verification for G1 planned for March 2027.

# 3. Programmes and research

Questionnaire for Round 3 translated and back-translated into Sinhala and Tamil; cognitive pre-test completed.

Two district-level permissions still pending; fieldwork partner has re-sequenced districts.

Concept notes for the eight dimensions under internal review before the methodology partner's comments in December.

Policy brief on economic fairness and trust planned for February 2027.

# 4. Outreach and communications

Four of six community dialogues held; two moved to November because of the monsoon.

Media workshop held for 22 journalists; second workshop planned for January.

Website traffic up after the Round 2 data release; social media spend lower than planned.

# 5. People and organisation

Team of nine. Communications Officer joined in February; second Research Assistant joined in April.

Microsoft 365 Copilot licences purchased (5). Adoption programme starting November with an external consultant.

Draft AI use policy prepared – see decision 3.

# 6. Key risks

| Risk | Rating | Mitigation |
| --- | --- | --- |
| Funding concentration – one donor provides about 70% of income | High | Funding diversification plan; 3 concept notes to new funders by Q2 2027 |
| Fieldwork delay affects report timeline | Medium | Re-sequenced districts; no-cost extension discussion with donor if needed |
| Respondent data exposure | Medium | Restricted storage, anonymisation before analysis, sensitivity labels, AI use policy |
| Cash shortfall Dec–Jan | Medium | Defer non-essential spend; early submission of interim report |
| Exchange rate movement | Low | Monitor monthly; report at actual rates as required |

# 7. Decisions requested from the Board

Approve the Reserves Policy (target: 3 months of operating costs within 3 years).

Note the possible no-cost extension request for G1 (decision in February).

Approve the AI Use Policy and the Copilot pilot (5 licences, 6-month review).

Approve the 2027 board meeting calendar.