## README
Grant Budget Monitoring – FY2026 (Jan–Dec)
FICTIONAL SAMPLE DATA — created for a Microsoft 365 Copilot demo. Not real Insights data.
Organisation | The Insights Initiative (sample)
Financial year | 1 January – 31 December 2026
Actuals to | 31 October 2026 (10 of 12 months; expected burn to date = 83.3%)
Currency | Sri Lankan Rupees (LKR)
Grants | G1 – SLB Survey Round & Follow-up Research ¦ G2 – Young Researchers Programme ¦ G3 – Outreach, Media & Dialogue
Donor budget rate | EUR 1 = LKR 330 (illustrative)
Variance rule | Donor requires an explanation for any budget line more than 10% over or under the expected spend
Sheets | Budget_vs_Actual • Ledger_2026 • Shared_Costs • Cash_Flow_Forecast
Prepared by | Finance & Administration (FAM)
Status | DRAFT – not yet reviewed

## Budget_vs_Actual
Grant | Grant name | Line code | Budget line | Category | Annual budget (LKR) | YTD actual (LKR) | Notes from programme team
G1 | SLB Survey Round & Follow-up Research | 1.01 | Research Lead (ED) – 40% FTE | Personnel | 3840000 | 3198700
G1 | SLB Survey Round & Follow-up Research | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | 3300000 | 2748900
G1 | SLB Survey Round & Follow-up Research | 1.03 | Research Expert – 100% FTE | Personnel | 4200000 | 3498600
G1 | SLB Survey Round & Follow-up Research | 1.04 | Research Assistants x2 – 100% FTE | Personnel | 3600000 | 2520000 | RA2 joined in April after vacancy
G1 | SLB Survey Round & Follow-up Research | 1.05 | Survey fieldwork – data collection contract | Activities | 18500000 | 10175000 | Fieldwork tranche 2 delayed – permissions in two districts
G1 | SLB Survey Round & Follow-up Research | 1.06 | Questionnaire translation & back-translation (S/T) | Activities | 850000 | 952000
G1 | SLB Survey Round & Follow-up Research | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | 2400000 | 2184000
G1 | SLB Survey Round & Follow-up Research | 1.08 | Transcription & anonymisation services | Activities | 1200000 | 1674400
G1 | SLB Survey Round & Follow-up Research | 1.09 | International methodology advisory | Professional fees | 2600000 | 2158000
G1 | SLB Survey Round & Follow-up Research | 1.10 | Data analysis software licences | Equipment & software | 450000 | 450000
G1 | SLB Survey Round & Follow-up Research | 1.11 | Domestic travel – research team | Travel | 1100000 | 858000
G1 | SLB Survey Round & Follow-up Research | 1.12 | Report design, editing & printing | Communications | 1350000 | 297000 | Final report due Q1 2027
G1 | SLB Survey Round & Follow-up Research | 1.13 | Shared office costs (allocated) | Shared costs | 2280000 | 1899200
G2 | Young Researchers Programme | 2.01 | Programme Officer – 30% FTE | Personnel | 1080000 | 899600
G2 | Young Researchers Programme | 2.02 | Young researcher stipends x8 | Activities | 3200000 | 3040000
G2 | Young Researchers Programme | 2.03 | Mentoring workshops x3 | Activities | 1500000 | 1770000
G2 | Young Researchers Programme | 2.04 | Field visit travel – young researchers | Travel | 900000 | 1206000
G2 | Young Researchers Programme | 2.05 | Research publication & launch event | Communications | 1100000 | 165000 | Launch planned for February 2027
G2 | Young Researchers Programme | 2.06 | Partner coordination fee | Professional fees | 750000 | 500200
G2 | Young Researchers Programme | 2.07 | Shared office costs (allocated) | Shared costs | 684000 | 569800
G3 | Outreach, Media & Dialogue | 3.01 | Communications Officer – 100% FTE | Personnel | 2640000 | 1980000 | Comms Officer started February
G3 | Outreach, Media & Dialogue | 3.02 | Community dialogues – 6 provinces | Activities | 3600000 | 2304000 | Two dialogues moved to November
G3 | Outreach, Media & Dialogue | 3.03 | Media workshops for journalists x2 | Activities | 1800000 | 1890000
G3 | Outreach, Media & Dialogue | 3.04 | Translation of outputs (Sinhala/Tamil) | Communications | 960000 | 1161600
G3 | Outreach, Media & Dialogue | 3.05 | Social media boosting & video production | Communications | 1200000 | 576000
G3 | Outreach, Media & Dialogue | 3.06 | Website maintenance & hosting | Equipment & software | 360000 | 299900
G3 | Outreach, Media & Dialogue | 3.07 | Domestic travel – outreach | Travel | 840000 | 1083600
G3 | Outreach, Media & Dialogue | 3.08 | Shared office costs (allocated) | Shared costs | 1596000 | 1329500

## Ledger_2026
Date | Voucher no | Grant | Line code | Budget line | Category | Description | Payee (coded) | Amount (LKR) | Payment method | Receipt ref
2026-01-07 | PV-2026-0001 | G2 | 2.03 | Mentoring workshops x3 | Activities | Invoice – Mentoring workshops x3 | Hotel venue V-027 | 602700 | Bank transfer | RCPT-56821
2026-01-10 | PV-2026-0002 | G3 | 3.02 | Community dialogues – 6 provinces | Activities | Settlement – Community dialogues | Outreach partner V-011 | 1138500 | Bank transfer | RCPT-27564
2026-01-10 | PV-2026-0003 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 72900 | Bank transfer | RCPT-60936
2026-01-10 | PV-2026-0004 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Jan 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-34732
2026-01-16 | PV-2026-0005 | G1 | 1.08 | Transcription & anonymisation services | Activities | Advance – Transcription & anonymisation services | Transcription V-031 | 162400 | Bank transfer | RCPT-92551
2026-01-16 | PV-2026-0006 | G1 | 1.08 | Transcription & anonymisation services | Activities | Final payment – Transcription & anonymisation services | Transcription V-031 | 145000 | Bank transfer | RCPT-11238
2026-01-16 | PV-2026-0007 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Jan 2026 | Shared cost allocation | 189900 | Bank transfer | RCPT-89423
2026-01-18 | PV-2026-0008 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Jan 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-94906
2026-01-18 | PV-2026-0009 | G1 | 1.08 | Transcription & anonymisation services | Activities | Advance – Transcription & anonymisation services | Transcription V-031 | 162400 | Bank transfer | RCPT-72916
2026-01-19 | PV-2026-0010 | G3 | 3.03 | Media workshops for journalists x2 | Activities | Final payment – Media workshops for journalists x2 | Media trainer V-016 | 1052200 | Bank transfer | RCPT-65397
2026-01-20 | PV-2026-0011 | G2 | 2.05 | Research publication & launch event | Communications | Invoice – Research publication & launch event | Design studio V-018 | 42000 | Bank transfer | RCPT-56616
2026-01-22 | PV-2026-0012 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Jan 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-80434
2026-01-22 | PV-2026-0013 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Jan 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-32398
2026-01-23 | PV-2026-0014 | G1 | 1.09 | International methodology advisory | Professional fees | Invoice – International methodology advisory | Methodology partner V-005 | 1010200 | Bank transfer | RCPT-77658
2026-01-24 | PV-2026-0015 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 54300 | Bank transfer | RCPT-13868
2026-01-25 | PV-2026-0016 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Jan 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-33543
2026-01-25 | PV-2026-0017 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Jan 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-51244
2026-01-25 | PV-2026-0018 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Jan 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-80660
2026-01-25 | PV-2026-0019 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Jan 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-28972
2026-02-02 | PV-2026-0020 | G1 | 1.06 | Questionnaire translation & back-translation (S/T) | Activities | Settlement – Questionnaire translation & back-translation (S/T) | Translator V-022 | 206500 | Bank transfer | RCPT-31487
2026-02-02 | PV-2026-0021 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 45800 | Bank transfer | RCPT-13724
2026-02-06 | PV-2026-0022 | G1 | 1.09 | International methodology advisory | Professional fees | Invoice – International methodology advisory | Methodology partner V-005 | 1147800 | Bank transfer | RCPT-25295
2026-02-07 | PV-2026-0023 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Feb 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-77501
2026-02-09 | PV-2026-0024 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 39700 | Bank transfer | RCPT-97517
2026-02-09 | PV-2026-0025 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Feb 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-94332
2026-02-11 | PV-2026-0026 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Feb 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-10261
2026-02-12 | PV-2026-0027 | G1 | 1.10 | Data analysis software licences | Equipment & software | Invoice – Data analysis software licences | Software reseller V-040 | 450000 | Bank transfer | RCPT-59093
2026-02-12 | PV-2026-0028 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Feb 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-18336
2026-02-14 | PV-2026-0029 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Final payment – Focus group discussions | Various – FGD logistics | 132200 | Bank transfer | RCPT-58234
2026-02-14 | PV-2026-0030 | G1 | 1.11 | Domestic travel – research team | Travel | Vehicle hire – Jaffna field visit | Various – travel | 93400 | Bank transfer | RCPT-49668
2026-02-15 | PV-2026-0031 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Settlement – Focus group discussions | Various – FGD logistics | 220300 | Bank transfer | RCPT-38336
2026-02-19 | PV-2026-0032 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 31000 | Bank transfer | RCPT-79747
2026-02-21 | PV-2026-0033 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Feb 2026 | Shared cost allocation | 189900 | Bank transfer | RCPT-30214
2026-02-25 | PV-2026-0034 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Feb 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-88577
2026-02-25 | PV-2026-0035 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Feb 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-89956
2026-02-25 | PV-2026-0036 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Feb 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-42526
2026-02-25 | PV-2026-0037 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Feb 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-26583
2026-02-25 | PV-2026-0038 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – Feb 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-23928
2026-03-03 | PV-2026-0039 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Mar 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-52767
2026-03-03 | PV-2026-0040 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Mar 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-73512
2026-03-05 | PV-2026-0041 | G1 | 1.11 | Domestic travel – research team | Travel | Per diem – Matara | Various – travel | 67100 | Bank transfer | RCPT-24076
2026-03-08 | PV-2026-0042 | G2 | 2.04 | Field visit travel – young researchers | Travel | Bus/train fares – Galle | Various – travel | 191200 | Bank transfer | RCPT-19585
2026-03-09 | PV-2026-0043 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Mar 2026 | Shared cost allocation | 189900 | Bank transfer | RCPT-59964
2026-03-10 | PV-2026-0044 | G2 | 2.04 | Field visit travel – young researchers | Travel | Vehicle hire – Batticaloa | Various – travel | 218000 | Bank transfer | RCPT-44415
2026-03-10 | PV-2026-0045 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Mar 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-90865
2026-03-12 | PV-2026-0046 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 43400 | Bank transfer | RCPT-49517
2026-03-13 | PV-2026-0047 | G2 | 2.06 | Partner coordination fee | Professional fees | Invoice – Partner coordination fee | Research partner V-009 | 256900 | Bank transfer | RCPT-94875
2026-03-14 | PV-2026-0048 | G2 | 2.03 | Mentoring workshops x3 | Activities | Final payment – Mentoring workshops x3 | Hotel venue V-027 | 497300 | Bank transfer | RCPT-25407
2026-03-15 | PV-2026-0049 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 45300 | Bank transfer | RCPT-55586
2026-03-16 | PV-2026-0050 | G1 | 1.08 | Transcription & anonymisation services | Activities | Invoice – Transcription & anonymisation services | Transcription V-031 | 158700 | Bank transfer | RCPT-72178
2026-03-17 | PV-2026-0051 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Mar 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-75372
2026-03-18 | PV-2026-0052 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Advance – Focus group discussions | Various – FGD logistics | 142000 | Bank transfer | RCPT-25851
2026-03-25 | PV-2026-0053 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Mar 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-82822
2026-03-25 | PV-2026-0054 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Mar 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-78019
2026-03-25 | PV-2026-0055 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Mar 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-42378
2026-03-25 | PV-2026-0056 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Mar 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-57012
2026-03-25 | PV-2026-0057 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – Mar 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-99592
2026-04-03 | PV-2026-0058 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Apr 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-69760
2026-04-04 | PV-2026-0059 | G1 | 1.11 | Domestic travel – research team | Travel | Vehicle hire – Jaffna field visit | Various – travel | 64600 | Bank transfer | RCPT-86718
2026-04-06 | PV-2026-0060 | G3 | 3.07 | Domestic travel – outreach | Travel | Vehicle hire – Batticaloa | Various – travel | 70500 | Bank transfer | RCPT-55235
2026-04-12 | PV-2026-0061 | G3 | 3.03 | Media workshops for journalists x2 | Activities | Settlement – Media workshops for journalists x2 | Media trainer V-016 | 837800 | Bank transfer | RCPT-20819
2026-04-13 | PV-2026-0062 | G3 | 3.04 | Translation of outputs (Sinhala/Tamil) | Communications | Invoice – Translation of outputs (Sinhala/Tamil) | Translator V-022 | 193100 | Bank transfer | RCPT-19048
2026-04-15 | PV-2026-0063 | G1 | 1.08 | Transcription & anonymisation services | Activities | Settlement – Transcription & anonymisation services | Transcription V-031 | 95600 | Bank transfer | RCPT-21516
2026-04-15 | PV-2026-0064 | G2 | 2.03 | Mentoring workshops x3 | Activities | Settlement – Mentoring workshops x3 | Hotel venue V-027 | 670000 | Bank transfer | RCPT-74856
2026-04-19 | PV-2026-0065 | G3 | 3.07 | Domestic travel – outreach | Travel | Per diem – Trincomalee visit | Various – travel | 87000 | Bank transfer | RCPT-50897
2026-04-20 | PV-2026-0066 | G2 | 2.05 | Research publication & launch event | Communications | Invoice – Research publication & launch event | Design studio V-018 | 31600 | Bank transfer | RCPT-44773
2026-04-20 | PV-2026-0067 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Apr 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-96783
2026-04-22 | PV-2026-0068 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Apr 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-39628
2026-04-22 | PV-2026-0069 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 63200 | Bank transfer | RCPT-32064
2026-04-23 | PV-2026-0070 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Apr 2026 | Shared cost allocation | 189900 | Bank transfer | RCPT-52598
2026-04-25 | PV-2026-0071 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Apr 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-66701
2026-04-25 | PV-2026-0072 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Apr 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-76358
2026-04-25 | PV-2026-0073 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Apr 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-83606
2026-04-25 | PV-2026-0074 | G1 | 1.04 | Research Assistants x2 – 100% FTE | Personnel | Salary & EPF/ETF – Apr 2026 | Payroll – RA1/RA2 | 360000 | Bank transfer | RCPT-53478
2026-04-25 | PV-2026-0075 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Apr 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-52296
2026-04-25 | PV-2026-0076 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – Apr 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-96120
2026-04-25 | PV-2026-0077 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Apr 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-74643
2026-05-02 | PV-2026-0078 | G2 | 2.04 | Field visit travel – young researchers | Travel | Vehicle hire – Batticaloa | Various – travel | 114500 | Bank transfer | RCPT-62831
2026-05-02 | PV-2026-0079 | G3 | 3.07 | Domestic travel – outreach | Travel | Fuel – Kurunegala | Various – travel | 97500 | Bank transfer | RCPT-51114
2026-05-04 | PV-2026-0080 | G1 | 1.08 | Transcription & anonymisation services | Activities | Final payment – Transcription & anonymisation services | Transcription V-031 | 77800 | Bank transfer | RCPT-33166
2026-05-04 | PV-2026-0081 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – May 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-35753
2026-05-05 | PV-2026-0082 | G1 | 1.08 | Transcription & anonymisation services | Activities | Invoice – Transcription & anonymisation services | Transcription V-031 | 107500 | Bank transfer | RCPT-70687
2026-05-09 | PV-2026-0083 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – May 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-38858
2026-05-13 | PV-2026-0084 | G1 | 1.11 | Domestic travel – research team | Travel | Vehicle hire – Anuradhapura | Various – travel | 130400 | Bank transfer | RCPT-55684
2026-05-16 | PV-2026-0085 | G2 | 2.04 | Field visit travel – young researchers | Travel | Vehicle hire – Anuradhapura | Various – travel | 98400 | Bank transfer | RCPT-55888
2026-05-17 | PV-2026-0086 | G1 | 1.08 | Transcription & anonymisation services | Activities | Final payment – Transcription & anonymisation services | Transcription V-031 | 132600 | Bank transfer | RCPT-63700
2026-05-19 | PV-2026-0087 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – May 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-87314
2026-05-20 | PV-2026-0088 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Invoice – Focus group discussions | Various – FGD logistics | 157100 | Bank transfer | RCPT-60020
2026-05-20 | PV-2026-0089 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – May 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-37902
2026-05-24 | PV-2026-0090 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – May 2026 | Shared cost allocation | 189900 | Bank transfer | RCPT-30234
2026-05-25 | PV-2026-0091 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – May 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-67890
2026-05-25 | PV-2026-0092 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – May 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-84261
2026-05-25 | PV-2026-0093 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – May 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-96093
2026-05-25 | PV-2026-0094 | G1 | 1.04 | Research Assistants x2 – 100% FTE | Personnel | Salary & EPF/ETF – May 2026 | Payroll – RA1/RA2 | 360000 | Bank transfer | RCPT-26722
2026-05-25 | PV-2026-0095 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – May 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-66530
2026-05-25 | PV-2026-0096 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – May 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-45078
2026-05-26 | PV-2026-0097 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Invoice – Focus group discussions | Various – FGD logistics | 96600 | Bank transfer | RCPT-53119
2026-06-03 | PV-2026-0098 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Advance – Focus group discussions | Various – FGD logistics | 227400 | Bank transfer | RCPT-25446
2026-06-03 | PV-2026-0099 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Jun 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-51947
2026-06-04 | PV-2026-0100 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Jun 2026 | Shared cost allocation | 189900 | Bank transfer
2026-06-05 | PV-2026-0101 | G1 | 1.05 | Survey fieldwork – data collection contract | Activities | Invoice – Survey fieldwork | Survey firm V-014 | 5586900 | Bank transfer | RCPT-44924
2026-06-07 | PV-2026-0102 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 57500 | Bank transfer
2026-06-08 | PV-2026-0103 | G3 | 3.07 | Domestic travel – outreach | Travel | Per diem – Trincomalee visit | Various – travel | 105400 | Bank transfer | RCPT-68254
2026-06-11 | PV-2026-0104 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Jun 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-44553
2026-06-14 | PV-2026-0105 | G3 | 3.07 | Domestic travel – outreach | Travel | Per diem – Matara | Various – travel | 91500 | Bank transfer | RCPT-29052
2026-06-15 | PV-2026-0106 | G2 | 2.04 | Field visit travel – young researchers | Travel | Fuel – Kurunegala | Various – travel | 148200 | Bank transfer | RCPT-81449
2026-06-20 | PV-2026-0107 | G3 | 3.07 | Domestic travel – outreach | Travel | Vehicle hire – Jaffna field visit | Various – travel | 54100 | Bank transfer | RCPT-92165
2026-06-23 | PV-2026-0108 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Jun 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-45150
2026-06-23 | PV-2026-0109 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Jun 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-40709
2026-06-25 | PV-2026-0110 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Jun 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-53485
2026-06-25 | PV-2026-0111 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Jun 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-28804
2026-06-25 | PV-2026-0112 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Jun 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-83570
2026-06-25 | PV-2026-0113 | G1 | 1.04 | Research Assistants x2 – 100% FTE | Personnel | Salary & EPF/ETF – Jun 2026 | Payroll – RA1/RA2 | 360000 | Bank transfer | RCPT-26152
2026-06-25 | PV-2026-0114 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Jun 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-45115
2026-06-25 | PV-2026-0115 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – Jun 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-48465
2026-06-25 | PV-2026-0116 | G3 | 3.04 | Translation of outputs (Sinhala/Tamil) | Communications | Invoice – Translation of outputs (Sinhala/Tamil) | Translator V-022 | 179900 | Bank transfer | RCPT-85286
2026-07-02 | PV-2026-0117 | G3 | 3.02 | Community dialogues – 6 provinces | Activities | Advance – Community dialogues | Outreach partner V-011 | 1165500 | Bank transfer | RCPT-70039
2026-07-02 | PV-2026-0118 | G3 | 3.04 | Translation of outputs (Sinhala/Tamil) | Communications | Invoice – Translation of outputs (Sinhala/Tamil) | Translator V-022 | 154900 | Bank transfer | RCPT-92993
2026-07-06 | PV-2026-0119 | G1 | 1.08 | Transcription & anonymisation services | Activities | Settlement – Transcription & anonymisation services | Transcription V-031 | 110900 | Bank transfer | RCPT-62591
2026-07-12 | PV-2026-0120 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Jul 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-62356
2026-07-16 | PV-2026-0121 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Jul 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-12846
2026-07-18 | PV-2026-0122 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Jul 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-82054
2026-07-19 | PV-2026-0123 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Jul 2026 | Shared cost allocation | 189900 | Bank transfer | RCPT-53144
2026-07-22 | PV-2026-0124 | G2 | 2.06 | Partner coordination fee | Professional fees | Invoice – Partner coordination fee | Research partner V-009 | 243300 | Bank transfer | RCPT-98357
2026-07-24 | PV-2026-0125 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Settlement – Focus group discussions | Various – FGD logistics | 172400 | Bank transfer | RCPT-63694
2026-07-24 | PV-2026-0126 | G3 | 3.04 | Translation of outputs (Sinhala/Tamil) | Communications | Invoice – Translation of outputs (Sinhala/Tamil) | Translator V-022 | 177700 | Bank transfer | RCPT-54149
2026-07-25 | PV-2026-0127 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Jul 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-22452
2026-07-25 | PV-2026-0128 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Jul 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-99020
2026-07-25 | PV-2026-0129 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Jul 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-74839
2026-07-25 | PV-2026-0130 | G1 | 1.04 | Research Assistants x2 – 100% FTE | Personnel | Salary & EPF/ETF – Jul 2026 | Payroll – RA1/RA2 | 360000 | Bank transfer | RCPT-98893
2026-07-25 | PV-2026-0131 | G1 | 1.08 | Transcription & anonymisation services | Activities | Settlement – Transcription & anonymisation services | Transcription V-031 | 140900 | Bank transfer | RCPT-92966
2026-07-25 | PV-2026-0132 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Jul 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-97507
2026-07-25 | PV-2026-0133 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – Jul 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-81619
2026-07-27 | PV-2026-0134 | G2 | 2.04 | Field visit travel – young researchers | Travel | Vehicle hire – community dialogue, Ampara (outreach) | Various – travel | 137300 | Bank transfer | RCPT-77723
2026-07-27 | PV-2026-0135 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Jul 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-37513
2026-08-02 | PV-2026-0136 | G1 | 1.08 | Transcription & anonymisation services | Activities | Advance – Transcription & anonymisation services | Transcription V-031 | 103900 | Bank transfer | RCPT-65631
2026-08-02 | PV-2026-0137 | G2 | 2.04 | Field visit travel – young researchers | Travel | Vehicle hire – Anuradhapura | Various – travel | 149400 | Bank transfer | RCPT-56158
2026-08-06 | PV-2026-0138 | G1 | 1.12 | Report design, editing & printing | Communications | Invoice – Report design, editing & printing | Design studio V-018 | 136500 | Bank transfer | RCPT-94964
2026-08-06 | PV-2026-0139 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Aug 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-53312
2026-08-07 | PV-2026-0140 | G2 | 2.04 | Field visit travel – young researchers | Travel | Vehicle hire – Anuradhapura | Various – travel | 149000 | Bank transfer | RCPT-17868
2026-08-07 | PV-2026-0141 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Aug 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-62397
2026-08-08 | PV-2026-0142 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Aug 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-32671
2026-08-11 | PV-2026-0143 | G3 | 3.04 | Translation of outputs (Sinhala/Tamil) | Communications | Invoice – Translation of outputs (Sinhala/Tamil) | Translator V-022 | 154200 | Bank transfer | RCPT-11378
2026-08-14 | PV-2026-0144 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Aug 2026 | Shared cost allocation | 189900 | Bank transfer | RCPT-45003
2026-08-17 | PV-2026-0145 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Invoice – Focus group discussions | Various – FGD logistics | 223500 | Bank transfer | RCPT-83258
2026-08-18 | PV-2026-0146 | G3 | 3.07 | Domestic travel – outreach | Travel | Vehicle hire – Batticaloa | Various – travel | 97200 | Bank transfer | RCPT-43052
2026-08-19 | PV-2026-0147 | G3 | 3.07 | Domestic travel – outreach | Travel | Fuel – Kurunegala | Various – travel | 155800 | Bank transfer | RCPT-27117
2026-08-23 | PV-2026-0148 | G1 | 1.06 | Questionnaire translation & back-translation (S/T) | Activities | Final payment – Questionnaire translation & back-translation (S/T) | Translator V-022 | 228000 | Bank transfer | RCPT-53779
2026-08-25 | PV-2026-0149 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Aug 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-85884
2026-08-25 | PV-2026-0150 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Aug 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-94458
2026-08-25 | PV-2026-0151 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Aug 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-90178
2026-08-25 | PV-2026-0152 | G1 | 1.04 | Research Assistants x2 – 100% FTE | Personnel | Salary & EPF/ETF – Aug 2026 | Payroll – RA1/RA2 | 360000 | Bank transfer | RCPT-64345
2026-08-25 | PV-2026-0153 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Aug 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-72382
2026-08-25 | PV-2026-0154 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – Aug 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-73296
2026-08-26 | PV-2026-0155 | G1 | 1.11 | Domestic travel – research team | Travel | Vehicle hire – Jaffna field visit | Various – travel | 110500 | Bank transfer | RCPT-54400
2026-08-26 | PV-2026-0156 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Aug 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-11540
2026-08-27 | PV-2026-0157 | G3 | 3.07 | Domestic travel – outreach | Travel | Fuel & driver allowance – Kandy | Various – travel | 109500 | Bank transfer | RCPT-14914
2026-09-02 | PV-2026-0158 | G1 | 1.08 | Transcription & anonymisation services | Activities | Settlement – Transcription & anonymisation services | Transcription V-031 | 129400 | Bank transfer | RCPT-38818
2026-09-02 | PV-2026-0159 | G1 | 1.11 | Domestic travel – research team | Travel | Fuel – Kurunegala | Various – travel | 102500 | Bank transfer | RCPT-93397
2026-09-03 | PV-2026-0160 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Sep 2026 | Shared cost allocation | 189900 | Bank transfer | RCPT-25838
2026-09-04 | PV-2026-0161 | G3 | 3.07 | Domestic travel – outreach | Travel | Fuel & driver allowance – Kandy | Various – travel | 57500 | Bank transfer | RCPT-96596
2026-09-05 | PV-2026-0162 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Settlement – Focus group discussions | Various – FGD logistics | 212900 | Bank transfer | RCPT-45211
2026-09-07 | PV-2026-0163 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Sep 2026 | Shared cost allocation | 133000 | Bank transfer | RCPT-52809
2026-09-08 | PV-2026-0164 | G1 | 1.06 | Questionnaire translation & back-translation (S/T) | Activities | Settlement – Questionnaire translation & back-translation (S/T) | Translator V-022 | 284700 | Bank transfer | RCPT-12331
2026-09-10 | PV-2026-0165 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Sep 2026 | Shared cost allocation | 57000 | Bank transfer | RCPT-37423
2026-09-12 | PV-2026-0166 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 33800 | Bank transfer | RCPT-69917
2026-09-17 | PV-2026-0167 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Invoice – Focus group discussions | Various – FGD logistics | 151300 | Bank transfer | RCPT-77494
2026-09-17 | PV-2026-0168 | G1 | 1.11 | Domestic travel – research team | Travel | Vehicle hire – Anuradhapura | Various – travel | 90600 | Bank transfer | RCPT-46295
2026-09-20 | PV-2026-0169 | G1 | 1.08 | Transcription & anonymisation services | Activities | Advance – Transcription & anonymisation services | Transcription V-031 | 59300 | Bank transfer | RCPT-91635
2026-09-21 | PV-2026-0170 | G1 | 1.05 | Survey fieldwork – data collection contract | Activities | Settlement – Survey fieldwork | Survey firm V-014 | 4588100 | Bank transfer | RCPT-92597
2026-09-22 | PV-2026-0171 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Sep 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-58422
2026-09-22 | PV-2026-0172 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 63100 | Bank transfer | RCPT-20353
2026-09-23 | PV-2026-0173 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Settlement – Focus group discussions | Various – FGD logistics | 223400 | Bank transfer | RCPT-82845
2026-09-23 | PV-2026-0174 | G2 | 2.05 | Research publication & launch event | Communications | Invoice – Research publication & launch event | Design studio V-018 | 46000 | Bank transfer | RCPT-34596
2026-09-25 | PV-2026-0175 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Sep 2026 | Payroll – ED | 319900 | Bank transfer | RCPT-80642
2026-09-25 | PV-2026-0176 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Sep 2026 | Payroll – SMP | 274900 | Bank transfer | RCPT-11493
2026-09-25 | PV-2026-0177 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Sep 2026 | Payroll – REX | 349900 | Bank transfer | RCPT-22529
2026-09-25 | PV-2026-0178 | G1 | 1.04 | Research Assistants x2 – 100% FTE | Personnel | Salary & EPF/ETF – Sep 2026 | Payroll – RA1/RA2 | 360000 | Bank transfer | RCPT-30424
2026-09-25 | PV-2026-0179 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Sep 2026 | Payroll – PO | 90000 | Bank transfer | RCPT-53251
2026-09-25 | PV-2026-0180 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – Sep 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-38757
2026-09-25 | PV-2026-0181 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Sep 2026 | Web vendor V-038 | 30000 | Bank transfer | RCPT-70747
2026-09-25 | PV-2026-0182 | G3 | 3.07 | Domestic travel – outreach | Travel | Per diem – Matara | Various – travel | 72000 | Bank transfer | RCPT-37049
2026-10-03 | PV-2026-0183 | G3 | 3.05 | Social media boosting & video production | Communications | Invoice – Social media boosting & video production | Video producer V-035 | 26000 | Bank transfer | RCPT-89440
2026-10-05 | PV-2026-0184 | G2 | 2.05 | Research publication & launch event | Communications | Invoice – Research publication & launch event | Design studio V-018 | 45400 | Bank transfer | RCPT-98230
2026-10-08 | PV-2026-0185 | G1 | 1.13 | Shared office costs (allocated) | Shared costs | Shared office costs – Oct 2026 | Shared cost allocation | 190100 | Bank transfer | RCPT-32384
2026-10-08 | PV-2026-0186 | G2 | 2.02 | Young researcher stipends x8 | Activities | Young researcher stipends x8 – Oct 2026 | Stipends – YR cohort | 304000 | Bank transfer | RCPT-50559
2026-10-10 | PV-2026-0187 | G1 | 1.06 | Questionnaire translation & back-translation (S/T) | Activities | Final payment – Questionnaire translation & back-translation (S/T) | Translator V-022 | 232800 | Bank transfer | RCPT-21047
2026-10-10 | PV-2026-0188 | G2 | 2.07 | Shared office costs (allocated) | Shared costs | Shared office costs – Oct 2026 | Shared cost allocation | 56800 | Bank transfer | RCPT-84399
2026-10-11 | PV-2026-0189 | G3 | 3.04 | Translation of outputs (Sinhala/Tamil) | Communications | Invoice – Translation of outputs (Sinhala/Tamil) | Translator V-022 | 185800 | Bank transfer
2026-10-11 | PV-2026-0190 | G3 | 3.08 | Shared office costs (allocated) | Shared costs | Shared office costs – Oct 2026 | Shared cost allocation | 132500 | Bank transfer | RCPT-64662
2026-10-12 | PV-2026-0191 | G3 | 3.04 | Translation of outputs (Sinhala/Tamil) | Communications | Invoice – Translation of outputs (Sinhala/Tamil) | Translator V-022 | 116000 | Bank transfer | RCPT-78393
2026-10-12 | PV-2026-0192 | G3 | 3.07 | Domestic travel – outreach | Travel | Fuel – Kurunegala | Various – travel | 85600 | Bank transfer | RCPT-99278
2026-10-14 | PV-2026-0193 | G3 | 3.06 | Website maintenance & hosting | Equipment & software | Website maintenance & hosting – Oct 2026 | Web vendor V-038 | 29900 | Bank transfer | RCPT-87209
2026-10-15 | PV-2026-0194 | G1 | 1.12 | Report design, editing & printing | Communications | Invoice – Report design, editing & printing | Design studio V-018 | 160500 | Bank transfer | RCPT-83289
2026-10-16 | PV-2026-0195 | G1 | 1.11 | Domestic travel – research team | Travel | Vehicle hire – Anuradhapura | Various – travel | 132900 | Bank transfer | RCPT-27465
2026-10-21 | PV-2026-0196 | G1 | 1.08 | Transcription & anonymisation services | Activities | Invoice – Transcription & anonymisation services | Transcription V-031 | 88000 | Bank transfer | RCPT-24163
2026-10-23 | PV-2026-0197 | G1 | 1.11 | Domestic travel – research team | Travel | Per diem – Trincomalee visit | Various – travel | 66000 | Bank transfer | RCPT-13709
2026-10-24 | PV-2026-0198 | G1 | 1.07 | Focus group discussions – venues, travel, refreshments | Activities | Final payment – Focus group discussions | Various – FGD logistics | 224900 | Bank transfer | RCPT-45504
2026-10-25 | PV-2026-0199 | G1 | 1.01 | Research Lead (ED) – 40% FTE | Personnel | Salary & EPF/ETF – Oct 2026 | Payroll – ED | 319600 | Bank transfer | RCPT-64989
2026-10-25 | PV-2026-0200 | G1 | 1.02 | Senior Manager Programmes – 50% FTE | Personnel | Salary & EPF/ETF – Oct 2026 | Payroll – SMP | 274800 | Bank transfer | RCPT-15829
2026-10-25 | PV-2026-0201 | G1 | 1.03 | Research Expert – 100% FTE | Personnel | Salary & EPF/ETF – Oct 2026 | Payroll – REX | 349500 | Bank transfer | RCPT-34282
2026-10-25 | PV-2026-0202 | G1 | 1.04 | Research Assistants x2 – 100% FTE | Personnel | Salary & EPF/ETF – Oct 2026 | Payroll – RA1/RA2 | 360000 | Bank transfer | RCPT-82120
2026-10-25 | PV-2026-0203 | G2 | 2.01 | Programme Officer – 30% FTE | Personnel | Salary & EPF/ETF – Oct 2026 | Payroll – PO | 89600 | Bank transfer | RCPT-77295
2026-10-25 | PV-2026-0204 | G3 | 3.01 | Communications Officer – 100% FTE | Personnel | Salary & EPF/ETF – Oct 2026 | Payroll – CO | 220000 | Bank transfer | RCPT-40324

## Shared_Costs
Cost item | Basis of allocation | Monthly cost (LKR) | Annual cost (LKR) | G1 % | G2 % | G3 % | Core / unrestricted %
Office rent – Colombo 08 | Floor space | 285000 | 3420000 | 55% | 15% | 20% | 10%
Electricity & water | Floor space | 48000 | 576000 | 55% | 15% | 20% | 10%
Internet & telephone | Headcount | 22000 | 264000 | 50% | 15% | 25% | 10%
Microsoft 365 & Copilot licences | Headcount | [TBC] |  | 50% | 15% | 25% | 10%
Accounting software subscription | Transactions | 9500 | 114000 | 60% | 15% | 25% | 0%
Finance & Admin Manager – salary | Timesheets | [CONFIDENTIAL – see payroll] |  | 45% | 15% | 20% | 20%
Office assistant – salary | Headcount | [CONFIDENTIAL – see payroll] |  | 50% | 15% | 25% | 10%
External audit fee (annual) | Expenditure share | [TBC] |  | 60% | 15% | 20% | 5%
Insurance (office & equipment) | Floor space | 6500 | 78000 | 55% | 15% | 20% | 10%
Bank charges | Transactions | 7500 | 90000 | 60% | 10% | 20% | 5%
Office supplies & stationery | Headcount | 15000 | 180000 | 50% | 15% | 25% | 10%

## Cash_Flow_Forecast
Month | Opening balance | Donor tranche receipts | Other income | Personnel | Programme activities | Travel | Shared & admin | Closing balance | Comment
Nov 2026 | 14500000 | 0 | 150000 | 2050000 | 3900000 | 260000 | 480000 | 7960000 | Two community dialogues moved here
Dec 2026 | 7960000 | 0 | 0 | 2600000 | 1800000 | 120000 | 480000 | 2960000 | Includes 13th-month / festival advance
Jan 2027 | 2960000 | 0 | 0 | 2050000 | 900000 | 80000 | 1150000 | -1220000 | Audit fee; tranche 3 depends on interim report approval
Feb 2027 | -1220000 | 21500000 | 450000 | 2050000 | 4200000 | 300000 | 480000 | 13700000 | Tranche 3 expected (G1) – if interim report accepted
Mar 2027 | 13700000 | 0 | 0 | 2050000 | 3600000 | 280000 | 480000 | 7290000 | Fieldwork tranche 2 payment
Apr 2027 | 7290000 | 3200000 | 0 | 2050000 | 2400000 | 240000 | 480000 | 5320000 | G2 second instalment
May 2027 | 5320000 | 6000000 | 120000 | 2050000 | 1900000 | 200000 | 480000 | 6810000 | G3 second instalment
Jun 2027 | 6810000 | 0 | 0 | 2050000 | 1600000 | 180000 | 480000 | 2500000 | Report printing